## project_plan
Title | Description | Owner | Phase | Category | Status | Priority | Time Required (hrs) | Dependencies | Sprint
Stakeholder Interviews | Meet with all stakeholders to clarify needs and expectations | all | Requirements | Docs | Backlog | Must | 4 |  | Sprint 0
Define User Personas | Create user personas for UltraAdmin, ClientAdmin, Recruiter, Candidate | all | Requirements | Docs | Backlog | Must | 4 | Stakeholder Interviews | Sprint 0
Draft User Journeys | Map out user journeys for each role | all | Requirements | Docs | Backlog | Must | 4 | Define User Personas | Sprint 0
Write User Stories | Write and prioritize user stories for all features | all | Requirements | Docs | Backlog | Must | 4 | Draft User Journeys | Sprint 0
Finalize MVP Scope | Define MVP features using MoSCoW method | all | Requirements | Docs | Backlog | Must | 2 | Write User Stories | Sprint 0
Non-functional Requirements | Define performance, scaling, security, and compliance needs | all | Requirements | Docs | Backlog | Must | 3 | Finalize MVP Scope | Sprint 0
Document External Constraints | API rate limits, quotas, integration constraints | all | Requirements | Docs | Backlog | Must | 2 | Finalize MVP Scope | Sprint 0
Feasibility/Cost Study | Estimate technical feasibility and infra costs | all | Requirements | Docs | Backlog | Must | 3 | Finalize MVP Scope | Sprint 0
Design System Architecture | Draw component diagrams, select tech stack | all | Design | Backend | Backlog | Must | 6 | Non-functional Requirements | Sprint 1
Design DB Architecture | Design meta DB (tenants), per-tenant DB schema, migration plan | dev1 | Design | Backend | Backlog | Must | 5 | Design System Architecture | Sprint 1
Tenant Resolution Logic | Plan subdomain/JWT/header-based tenant routing | dev2 | Design | Backend | Backlog | Must | 4 | Design System Architecture | Sprint 1
API Contracts | Define REST endpoints and OpenAPI spec for all services | dev3 | Design | Backend | Backlog | Must | 6 | Design System Architecture | Sprint 1
Detailed UI Wireframes | Create wireframes for all major screens (Figma/MUI) | dev2 | Design | Frontend | Backlog | Must | 6 | Write User Stories | Sprint 1
Plan DevOps/CI Pipeline | Design CI/CD, backup, and monitoring plans | dev1 | Design | DevOps | Backlog | Must | 4 | Design System Architecture | Sprint 1
Draft Security Plan | Design auth, RBAC, tenant isolation, and encryption | dev3 | Design | Backend | Backlog | Must | 4 | Design System Architecture | Sprint 1
Setup Git/Repo | Setup monorepo (Nx optional), folders for backend/frontend/infra | all | Implementation | DevOps | Backlog | Must | 2 | Plan DevOps/CI Pipeline | Sprint 1
Backend Scaffold | NestJS app, core modules, dynamic DB, meta DB connection | dev1 | Implementation | Backend | Backlog | Must | 6 | Setup Git/Repo | Sprint 2
Frontend Scaffold | Vite + React + MUI, base pages/routes, theme provider | dev2 | Implementation | Frontend | Backlog | Must | 6 | Setup Git/Repo | Sprint 2
Infra Scaffold | Setup docker-compose for local (MongoDB x2, backend, frontend) | dev3 | Implementation | DevOps | Backlog | Must | 3 | Setup Git/Repo | Sprint 2
Create Meta DB Models | Mongoose models for tenants/admin users | dev1 | Implementation | Backend | Backlog | Must | 2 | Backend Scaffold | Sprint 2
Create Tenant Provisioning | Script/endpoint to create new DBs, register in meta DB | dev3 | Implementation | Backend | Backlog | Must | 4 | Create Meta DB Models | Sprint 2
Tenant Connection Middleware | Implement per-request DB context (NestJS) | dev1 | Implementation | Backend | Backlog | Must | 5 | Backend Scaffold | Sprint 2
UltraAdmin Features | Manage tenants, view logs, platform analytics | dev3 | Implementation | Backend | Backlog | Should | 6 | Tenant Connection Middleware | Sprint 3
Auth Module | JWT login, signup, per-tenant RBAC | dev2 | Implementation | Backend | Backlog | Must | 6 | Backend Scaffold | Sprint 2
User Module | CRUD users in tenant DB, assign roles | dev2 | Implementation | Backend | Backlog | Must | 4 | Auth Module | Sprint 3
Jobs Module | CRUD jobs, assign to recruiters | dev1 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
Candidates Module | CRUD, bulk import, status tracking | dev1 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
Campaigns Module | CRUD, schedule calls, AI script gen (OpenAI) | dev3 | Implementation | Backend | Backlog | Must | 6 | Backend Scaffold | Sprint 3
Real-Time Audio Module | Plivo media stream handling, Google STT/TTS | dev3 | Implementation | Backend | Backlog | Should | 8 | Campaigns Module | Sprint 3
Notifications Module | Email/SMS integration, campaign updates | dev2 | Implementation | Backend | Backlog | Should | 5 | Campaigns Module | Sprint 3
Knowledge Base Module | CRUD scripts/prompts per tenant | dev1 | Implementation | Backend | Backlog | Could | 4 | Jobs Module | Sprint 3
Audit Logs | Record sensitive actions per tenant | dev3 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
API Validation/Docs | Implement class-validator, OpenAPI docs | dev1 | Implementation | Backend | Backlog | Must | 3 | API Contracts | Sprint 3
Unit/Integration Tests | Write backend and frontend tests | all | Testing | Backend | Backlog | Must | 10 | All backend modules | Sprint 4
Frontend Auth Flows | Login/signup/Forgot password | dev2 | Implementation | Frontend | Backlog | Must | 5 | Frontend Scaffold | Sprint 3
Frontend Dashboard | Role-based nav/dashboard (UltraAdmin, ClientAdmin, Recruiter) | dev2 | Implementation | Frontend | Backlog | Must | 6 | Frontend Auth Flows | Sprint 3
Jobs/Recruiters Pages | Jobs list, create/edit jobs, assign recruiters | dev2 | Implementation | Frontend | Backlog | Must | 5 | Frontend Dashboard | Sprint 3
Candidate Pages | Candidate table, profile, transcript | dev1 | Implementation | Frontend | Backlog | Must | 6 | Frontend Dashboard | Sprint 3
Campaign Pages | Launch/manage campaigns, see AI call progress | dev3 | Implementation | Frontend | Backlog | Must | 6 | Frontend Dashboard | Sprint 3
Settings/Profile | User/org profile, notification preferences | dev2 | Implementation | Frontend | Backlog | Should | 4 | Frontend Dashboard | Sprint 4
Admin Tools | Meta tenant admin UI, backup/restore, logs | dev3 | Implementation | Frontend | Backlog | Could | 4 | Frontend Dashboard | Sprint 4
Notification UX | Consent banner, in-app/email/SMS settings | dev2 | Implementation | Frontend | Backlog | Should | 4 | Frontend Auth Flows | Sprint 4
Mobile Responsiveness | All pages mobile-ready (MUI) | all | Implementation | Frontend | Backlog | Should | 5 | All frontend modules | Sprint 4
Frontend Error/Empty UX | Graceful error and empty state screens | dev2 | Implementation | Frontend | Backlog | Must | 3 | All frontend modules | Sprint 4
End-to-End Tests | Cypress/Playwright E2E flows | all | Testing | Frontend | Backlog | Should | 8 | All frontend modules | Sprint 5
Load/Stress Testing | Simulate concurrent calls/campaigns | all | Testing | Backend | Backlog | Should | 8 | All backend modules | Sprint 5
Security Testing | Test for isolation, auth, XSS, etc. | all | Testing | Backend | Backlog | Must | 6 | All backend modules | Sprint 5
CI/CD Pipeline | Auto build/test/deploy (GitHub Actions) | dev1 | Deployment | DevOps | Backlog | Must | 5 | Plan DevOps/CI Pipeline | Sprint 5
K8s/Production Infra | Helm charts, scaling, secrets | dev3 | Deployment | DevOps | Backlog | Should | 6 | CI/CD Pipeline | Sprint 5
Monitoring & Alerts | Setup metrics/logs dashboards, alerting | dev1 | Deployment | DevOps | Backlog | Should | 5 | K8s/Production Infra | Sprint 5
Rollout & UAT | Release to pilot users, gather feedback | all | Deployment | Docs | Backlog | Must | 5 | All modules tested | Sprint 6
Docs & Training | Update READMEs, onboarding guides | all | Deployment | Docs | Backlog | Must | 4 | Rollout & UAT | Sprint 6
Continuous Improvement | Backlog grooming, team retros | all | Maintenance | Docs | Backlog | Must | 3 | Docs & Training | Sprint 6

## Plan_of_Action
Title | Description | Owner | Phase | Category | Status | Priority | Time Required (hrs) | Dependencies | Sprint
Kickoff Meeting | Formal project kickoff, align all team members and goals. | all | Initiation | Docs | Backlog | Must | 2 |  | Sprint 0
Stakeholder Interviews | Meet with all stakeholders to clarify requirements, pain points, and success criteria. | all | Requirement Analysis | Docs | Backlog | Must | 4 | Kickoff Meeting | Sprint 0
Define User Personas | Create user personas for UltraAdmin, ClientAdmin, Recruiter, Candidate. | all | Requirement Analysis | Docs | Backlog | Must | 4 | Stakeholder Interviews | Sprint 0
Draft User Journeys | Map out user journeys for each role (e.g., recruiter, candidate). | all | Requirement Analysis | Docs | Backlog | Must | 4 | Define User Personas | Sprint 0
Write User Stories | Write and prioritize user stories and acceptance criteria for all features. | all | Requirement Analysis | Docs | Backlog | Must | 4 | Draft User Journeys | Sprint 0
Finalize MVP Scope | Define MVP features and finalize scope using MoSCoW method. | all | Requirement Analysis | Docs | Backlog | Must | 2 | Write User Stories | Sprint 0
Document Non-functional Requirements | Define performance, scaling, security, and compliance requirements. | all | Requirement Analysis | Docs | Backlog | Must | 3 | Finalize MVP Scope | Sprint 0
Document Constraints | List all external constraints such as API rate limits, quotas, and integration limits. | all | Requirement Analysis | Docs | Backlog | Must | 2 | Finalize MVP Scope | Sprint 0
Feasibility/Cost Study | Estimate technical feasibility, infra/API costs, and timeline. | all | Requirement Analysis | Docs | Backlog | Must | 3 | Finalize MVP Scope | Sprint 0
Design System Architecture | Draw component diagrams, select stack, define services/modules and their interactions. | all | System Design | Backend | Backlog | Must | 6 | Document Non-functional Requirements | Sprint 1
Design Database Architecture | Design meta DB (tenants), per-tenant DB schema, and migration plan. | dev1 | System Design | Backend | Backlog | Must | 5 | Design System Architecture | Sprint 1
Plan Tenant Resolution Logic | Plan subdomain/JWT/header-based tenant routing and context injection. | dev2 | System Design | Backend | Backlog | Must | 4 | Design System Architecture | Sprint 1
Define API Contracts | Define REST endpoints and OpenAPI spec for all services. | dev3 | System Design | Backend | Backlog | Must | 6 | Design System Architecture | Sprint 1
Detailed UI Wireframes | Create wireframes for all major screens in Figma or MUI format. | dev2 | System Design | Frontend | Backlog | Must | 6 | Write User Stories | Sprint 1
Plan DevOps/CI Pipeline | Design CI/CD, backup, and monitoring plans for all environments. | dev1 | System Design | DevOps | Backlog | Must | 4 | Design System Architecture | Sprint 1
Draft Security Plan | Design authentication, RBAC, tenant isolation, and encryption approaches. | dev3 | System Design | Backend | Backlog | Must | 4 | Design System Architecture | Sprint 1
Setup Git/Monorepo | Setup monorepo (Nx optional), folders for backend, frontend, infra, and scripts. | all | Implementation | DevOps | Backlog | Must | 2 | Plan DevOps/CI Pipeline | Sprint 1
Backend Scaffold | NestJS app with dynamic DB, meta DB connection, and core modules. | dev1 | Implementation | Backend | Backlog | Must | 6 | Setup Git/Monorepo | Sprint 2
Frontend Scaffold | Vite + React + MUI with base pages/routes and theme provider. | dev2 | Implementation | Frontend | Backlog | Must | 6 | Setup Git/Monorepo | Sprint 2
Infra Scaffold | Setup docker-compose for local: multiple MongoDB, backend, frontend. | dev3 | Implementation | DevOps | Backlog | Must | 3 | Setup Git/Monorepo | Sprint 2
Create Meta DB Models | Mongoose models for tenants and admin users in meta DB. | dev1 | Implementation | Backend | Backlog | Must | 2 | Backend Scaffold | Sprint 2
Create Tenant Provisioning | Script/endpoint to create new DBs and register tenants in meta DB. | dev3 | Implementation | Backend | Backlog | Must | 4 | Create Meta DB Models | Sprint 2
Tenant Connection Middleware | Implement per-request DB context (NestJS middleware or interceptor). | dev1 | Implementation | Backend | Backlog | Must | 5 | Backend Scaffold | Sprint 2
UltraAdmin Features | Manage tenants, view logs, platform analytics in backend. | dev3 | Implementation | Backend | Backlog | Should | 6 | Tenant Connection Middleware | Sprint 3
Auth Module | JWT login, signup, per-tenant RBAC for users. | dev2 | Implementation | Backend | Backlog | Must | 6 | Backend Scaffold | Sprint 2
User Module | CRUD users in tenant DB, assign roles, manage access. | dev2 | Implementation | Backend | Backlog | Must | 4 | Auth Module | Sprint 3
Jobs Module | CRUD jobs, assign to recruiters, per-tenant data isolation. | dev1 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
Candidates Module | CRUD, bulk import, status tracking for candidates. | dev1 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
Campaigns Module | CRUD, schedule calls, AI script gen (OpenAI) for campaigns. | dev3 | Implementation | Backend | Backlog | Must | 6 | Backend Scaffold | Sprint 3
Real-Time Audio Module | Handle Plivo media stream, Google STT/TTS for real-time AI calls. | dev3 | Implementation | Backend | Backlog | Should | 8 | Campaigns Module | Sprint 3
Notifications Module | Integrate Email/SMS for campaign updates and reminders. | dev2 | Implementation | Backend | Backlog | Should | 5 | Campaigns Module | Sprint 3
Knowledge Base Module | CRUD scripts/prompts per tenant. | dev1 | Implementation | Backend | Backlog | Could | 4 | Jobs Module | Sprint 3
Audit Logs | Record sensitive actions per tenant for compliance. | dev3 | Implementation | Backend | Backlog | Must | 4 | Backend Scaffold | Sprint 3
API Validation & Docs | Implement class-validator, OpenAPI docs in backend. | dev1 | Implementation | Backend | Backlog | Must | 3 | Define API Contracts | Sprint 3
Unit/Integration Tests | Write backend and frontend unit/integration tests for all modules. | all | Testing | Backend | Backlog | Must | 10 | All backend modules | Sprint 4
Frontend Auth Flows | Build Login, Signup, Forgot password pages. | dev2 | Implementation | Frontend | Backlog | Must | 5 | Frontend Scaffold | Sprint 3
Frontend Dashboard | Role-based navigation/dashboard (UltraAdmin, ClientAdmin, Recruiter). | dev2 | Implementation | Frontend | Backlog | Must | 6 | Frontend Auth Flows | Sprint 3
Jobs/Recruiters Pages | Jobs list, create/edit jobs, assign recruiters. | dev2 | Implementation | Frontend | Backlog | Must | 5 | Frontend Dashboard | Sprint 3
Candidate Pages | Candidate table, profile, transcript views. | dev1 | Implementation | Frontend | Backlog | Must | 6 | Frontend Dashboard | Sprint 3
Campaign Pages | Launch/manage campaigns, see AI call progress. | dev3 | Implementation | Frontend | Backlog | Must | 6 | Frontend Dashboard | Sprint 3
Settings/Profile | User/org profile page, notification preferences. | dev2 | Implementation | Frontend | Backlog | Should | 4 | Frontend Dashboard | Sprint 4
Admin Tools | Meta tenant admin UI, backup/restore, logs. | dev3 | Implementation | Frontend | Backlog | Could | 4 | Frontend Dashboard | Sprint 4
Notification UX | Consent banner, in-app/email/SMS settings. | dev2 | Implementation | Frontend | Backlog | Should | 4 | Frontend Auth Flows | Sprint 4
Mobile Responsiveness | Ensure all pages are mobile-ready using MUI. | all | Implementation | Frontend | Backlog | Should | 5 | All frontend modules | Sprint 4
Frontend Error/Empty UX | Graceful error and empty state screens. | dev2 | Implementation | Frontend | Backlog | Must | 3 | All frontend modules | Sprint 4
End-to-End Tests | Cypress/Playwright E2E flows for all critical user journeys. | all | Testing | Frontend | Backlog | Should | 8 | All frontend modules | Sprint 5
Load/Stress Testing | Simulate concurrent calls/campaigns for backend and DB. | all | Testing | Backend | Backlog | Should | 8 | All backend modules | Sprint 5
Security Testing | Test for data isolation, auth, XSS, and other threats. | all | Testing | Backend | Backlog | Must | 6 | All backend modules | Sprint 5
CI/CD Pipeline | Auto build/test/deploy (GitHub Actions or other). | dev1 | Deployment | DevOps | Backlog | Must | 5 | Plan DevOps/CI Pipeline | Sprint 5
K8s/Production Infra | Helm charts, scaling, secrets for production deployment. | dev3 | Deployment | DevOps | Backlog | Should | 6 | CI/CD Pipeline | Sprint 5
Monitoring & Alerts | Setup metrics/log dashboards, uptime, error alerting. | dev1 | Deployment | DevOps | Backlog | Should | 5 | K8s/Production Infra | Sprint 5
Rollout & UAT | Release to pilot users, gather feedback and fix issues. | all | Deployment | Docs | Backlog | Must | 5 | All modules tested | Sprint 6
Docs & Training | Update READMEs, onboarding and user guides. | all | Deployment | Docs | Backlog | Must | 4 | Rollout & UAT | Sprint 6
Continuous Improvement | Regular backlog grooming, team retros, and maintenance. | all | Maintenance | Docs | Backlog | Must | 3 | Docs & Training | Sprint 6